**2018-2023 SHIP COMPLETIONS APPENDIX**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Name** | **Applicant** | **Number Of Units** | **Estimated Completion Date** | **Actual Completion Date** |
| Shore Road, Glencaple II | Building Craftsmen (Dumfries) | 2 | 31 Oct 2023 |  |
| Glencaple Near Dumfries (PSR) | Building Craftsmen (Dumfries) | 20 | 31 Oct 2023 |  |
| Devorgilla House Dumfries (PSR) | Building Craftsmen (Dumfries) | 12 | 19 Dec 2019 | 03 Mar 2020 |
| Annan Road Dumfries (PSR) | Building Craftsmen (Dumfries) | 14 | 28 Feb 2019 | 15 Feb 2019 |
| Hunterspark, Heathhall | Cunninghame Housing Association | 64 | 31 Oct 2023 |  |
| Hallmeadow Place, Annan | Cunninghame Housing Association | 130 | 26 Oct 2022 | 12 Oct 2022 |
| Windermere Park | Cunninghame Housing Association | 60 | 27 Sep 2022 | 22 Jul 2022 |
| Former Academy | Cunninghame Housing Association | 45 | 08 Oct 2021 | 04 Oct 2021 |
| Halcrow Stadium Phase 2 | Cunninghame Housing Association | 43 | 30 Mar 2020 | 30 Mar 2020 |
| AHSP Carrs Billington Site Annan | Cunninghame Housing Association | 27 | 01 Feb 2020 | 06 Mar 2020 |
| AHSP Halcrow Stadium Gretna | Cunninghame Housing Association | 47 | 31 Oct 2019 | 01 Oct 2019 |
| Purchase of 23 Longmeadow Avenue, Annan | Key Housing Association | 1 | 01 Dec 2023 |  |
| Conversion of 38 Millburn Court | Loreburn Housing Association | 1 | 28 Mar 2024 | 21 Aug 2023 |
| Academy Street, Castle Douglas | Loreburn Housing Association | 23 | 27 Nov 2023 |  |
| Station Road 2, Dalbeattie | Loreburn Housing Association | 16 | 31 Aug 2023 | 09 Aug 2023 |
| Longmeadow House, Annan | Loreburn Housing Association | 27 | 31 Aug 2023 | 21 Aug 2023 |
| Heathhall College Site, Herries Avenue | Loreburn Housing Association | 75 | 31 Aug 2022 | 27 Jul 2022 |
| Lincluden Church | Loreburn Housing Association | 13 | 10 Jan 2022 | 17 Jan 2022 |
| AHSP Nelsons Yard Annan | Loreburn Housing Association | 9 | 30 Jan 2021 | 09 Nov 2020 |
| Forsyth Street, Dumfries | Loreburn Housing Association | 4 | 29 Jan 2021 | 02 Mar 2021 |
| NHT Marchfield Robertson Homes | Loreburn Housing Association | 69 | 31 Mar 2020 | 20 Mar 2020 |
| College Mains, Dumfries | Loreburn Housing Association | 42 | 13 Dec 2019 | 09 Dec 2019 |
| AHSP Douglas Terr Castle Douglas | Loreburn Housing Association | 8 | 19 Nov 2018 | 03 Dec 2018 |
| EASTRIGGS - Gillwood Road | Wheatley Homes South | 18 | 29 Jul 2022 | 22 Jul 2022 |
| AHSP - Lincluden Depot Dumfries | Wheatley Homes South | 32 | 01 Mar 2022 | 21 Mar 2022 |
| Queensberry Square Sanquhar | Wheatley Homes South | 12 | 30 Jun 2021 | 29 Mar 2021 |
| AHSP - Monreith Phase 2 | Wheatley Homes South | 5 | 30 Apr 2021 | 24 May 2021 |
| AHSP Friars Vennel, Dumfires | Wheatley Homes South | 6 | 30 Nov 2018 | 05 Dec 2018 |
| GHIS - Queen Street, Dumfries | Wheatley Homes South | 3 | 31 Oct 2018 | 24 Oct 2018 |
| AHSP Lochfield Road Dumfries | Wheatley Homes South | 16 | 30 Sep 2018 | 09 Jul 2018 |
| AHSP - North Main Street Wigtown | Wheatley Homes South | 2 | 31 Mar 2018 | 08 Feb 2018 |